## Sheet1
Date | Main Features | Sub Features
Aug 14 ~ 20 | Registration | Sign in (UI, sign in api)
Sign up (UI, sign up api)
Forgot Password (UI:4, confirm email, send code, new pwd api)
Tip Screens(UI: 4)
Sign up - Update profile(UI, update profiel api)
Sign up - Sensor (UI: search, set sensor, update profile api)
Facebook Sign in / Sign up (Regist app to FB, fetch info , implement signin/sign up api)
Aug 21 ~ 27 | Training | Main Screen(5 Tabs)
Training Tab Screen(UI)
Combo/set/round training (upgrade UI from current version)
implement save/retrieve api
Show Training Result (combo/set/workout/overview)
import sensor module from current UI and clean
Aug 28 ~ Sep 3 | More(Profile) | Profile Tab(UI)
Main profile screen
Other profile screen
follower/following/challenge screen
follow/unfollow api and update UI
Sep 4 ~ Sep 10 | Profile | Edit Profile Screen and update API
update profile API
Contact US (UI, api)
Social Challenge(accept/decline api)
Statistics Screen (UI and api)
Acheivement Screen (UI and get acheivements api)
Sensor Manager screen(Search/Connect screens and update sensor api)
Notification Settings Screen(UI and update notification settings api)
Sep 11 ~ Sep 17 | Profile | implement push notification(Server setting, implement push in app)
My subscription
Store Screen
Help Center Screen
About Screen
Challenge History
Sep 18 ~ Sep 24 | Challenge | Challenge Screens(Main Screen, Battle Result/uncompleted battle, received battle, ,.. api)
Received Battles Screen(decline/accept)
Sent Battles (Resend battle)
Finished Battles
Battle Detail Screen
Battle Result Screen
New Battle Screen
Sep 25 ~ Oct 1 | Challenge | Select Battle Content Screen
Battle Description Screen
| Guidance | Videos Screen
play Video screen
Favorite/unfavorite video
favorite videos screen(search)
Oct 2 ~ Oct 8 | Messaging | Recent Message
Chat Screen
send/receive message
push notification
notification screen (implement apis)
Oct 9 ~ Oct 15 | Main Home Tab | Main Home Screen
Users feed screen
My progress screen
Analysis Screen
Calendar
Oct 16 ~ Oct 22 | Main Home Tab | Explore
Leaderboard
Follow/unfollow users
Search User and update UI
Tournaments Screen
Tournaments Leaderboard
Tournaments My Connection (invite connection to tournament)
Tournament Detail
Oct 23 ~ Oct 29 | In app purchase | Purchase Plans
Battle Purchase
Tutorial Purchase
Tournaments Purchase